## Sheet1
2025 State Employee Charitable Campaign Timeline
Date | Activity | By
2025
2025-01-01 | New Year's Day (State offices closed)
2025-01-14 | 89th Texas Legislature begins
2025-01-15 | Request is posted for applications from charities interested in participating in the SECC as statewide federations or members. | SCM
January 15 - March 10, 2025 | State Campaign Manager conducts administrative review of Statewide charity applications and notifies statewide charity federations of application review findings | SCM
2025-01-20 | Martin Luther King, Jr. Day (State offices closed)
2025-01-23 | Request is posted for applications from organizations interested in leading the SECC as Local Campaign Managers. | SCM
2025-01-24 | Deadline for Local Campaign Managers to submit final 2024 campaign results report to State Campaign Manager | LCM
January 15 - March 7, 2025 | State Campaign Manager conducts administrative review of Statewide charity applications and notifies statewide charity federations of application review findings | SCM
Week of February 2nd | LEC MEETINGS: Review 2025 Local Campaign Manager applications, budget, and nominate LEC Chair | LEC
2025-02-03 | Deadline for 2025 Local Campaign Manager applications and proposed budgets to be sent to Local Employee Committee Chair | LCM
2025-02-03 | Deadline for Local Campaign Managers to send any requests to produce local campaign materials to State Campaign Manager | LCM
2025-02-05 | Statutory deadline for State Campaign Manager to submit final statewide campaign results reporting to Comptroller, SPC, and SAC | SCM
2025-02-10 | SAC MEETING: Review proposed 2025 SCM campaign plan, timeline, and budget | SAC
2025-02-10 | LEC Chair sends recommended 2025 Local Campaign Manager, budget, and 2025 Local Employee Committee roster, including Chair to the SPC for approval | LEC
2025-02-10 | Application announcement is posted by Local Campaign Managers for local charities interested in participating in the SECC | LCM
February 10- March 21, 2025 | Local Campaign Managers conduct administrative review of local charity applications and notifies local charities of application review findings | LCM
2025-02-14 | SPC MEETING: Review SAC recommendation of SCM campaign plan, timeline, budget, and determine the SCM; review and approve 2025 local region names and boundaries; review and approve 2025 LCMs and budgets | SPC
2025-02-17 | Presidents' Day (State offices closed)
2025-02-18 | SPC submits 2025 SECC region names, boundaries, and LCM contact list to CPA and other SECC stakeholders | SCM
2025-02-18 | Conference call for 2025 Local Campaign Managers - local charity application training and annual campaign planning | SCM, LCM
2025-02-21 | Application deadline for charities applying as Statewide SECC charities, including 25-word descriptions and contribution impact information | STATEWIDE CHARITIES
February 10- March 21, 2025 | Local Campaign Managers conduct administrative review of local charity applications and notifies local charities of application review findings | LCM
January 15 - March 7, 2025 | State Campaign Manager conducts administrative review of Statewide charity applications and notifies statewide charity federations of application review findings | SCM
2025-03-02 | Texas Independence Day
2025-03-14 | SPC MEETING: 2025 SECC application review training, miscellaneous topics | SPC
2025-03-21 | Application deadline for charities applying as local SECC charities, including 25-word descriptions and contribution impact information | LOCAL CHARITIES
March 24 - April 28, 2025 | Local Employee Committees review local charity applications | LEC
2025-03-28 | First distribution of 2025 SECC funds to be finalized | LCM
2025-03-31 | Cesar Chavez Day (Optional state holiday)
March 24 - April 28, 2025 | Local Employee Committees review local charity applications | LEC
2025-04-10 | State Campaign Manager notifies statewide charity federations of application review findings | SCM
2025-04-10 | State Campaign Manager opens statewide charity applications to State Policy Committee for eligibility review | SCM
April 10 - 21, 2025 | State Policy Committee reviews statewide charity applications | SPC
2025-04-11 | SECC Honorary Chair(s) request letters sent to: Governor, Lt. Governor, and Speaker of the House | SCM
2025-04-16 | SECC Workshop & Roundtable webinar for all SECC stakeholders | ALL
2025-04-17 | SAC MEETING: Review proposed 2025 campaign materials and theme | SAC
2025-04-18 | Good Friday (Optional state holiday)
2025-04-21 | Application corrections due from Statewide charity federations | STATEWIDE CHARITIES
2025-04-21 | Deadline for Local Campaign Managers to submit final 2024 campaign results charity designation and donor information to other local SECC regions | LCM
2025-04-21 | San Jacinto Day (Skeleton crew required at state offices)
2025-04-22 | SPC MEETING: Determination of statewide charity eligibility, review and approve 2025 campaign materials, including any requests for locally produced materials; approve campaign theme(s) | SPC
2025-04-23 | SCM notifies SWFs of eligibility decisions by SPC | SCM
Week of April 27th | LEC MEETINGS: LECs meet to determine eligibility for all local 2025 SECC applicants and discuss materials/incentive items ordering | LEC
2025-04-28 | SWF eligibility appeals due to SCM | STATEWIDE CHARITIES
2025-04-29 | State Campaign Manager distributes statewide charity application appeals to State Policy Committee for eligibility review | SCM
April 29 - May 16, 2025 | State Policy Committee reviews statewide charity application appeals | SPC
April 29 - May 16, 2025 | State Policy Committee reviews statewide charity application appeals | SPC
Week of May 1st | Campaign ordering options made available to LCMs — incentives (via SCM) + print materials (via RJB) | SCM + RJB
2025-05-02 | Deadline for LCMs to send approval/denial letters to Local applicants (reasons for denial detailed) | LCM
2025-05-05 | Directory charity listing of approved/denied Local Organizations due to SCM | LCM
2025-05-09 | Deadline for corrections to local charities' applications | LOCAL CHARITIES
2025-05-09 | Local eligibility appeals due to SCM | LOCAL CHARITIES
May 9 - 15, 2025 | State Policy Committee reviews local charity application appeals | SPC
2025-05-16 | SPC MEETING: Review charity appeals for statewide and local charities and campaign planning | SPC
2025-05-16 | Deadline for SCM to submit finalized (Excel) spreadsheet of all approved 2025 charities (statewide and local) to print contractor for campaign materials production | SCM
Third week of May | Deadline for ordering campaign materials (print + incentives) through centralized ordering | LCM
2025-05-26 | Memorial Day (State offices closed)
2025-06-02 | 89th Texas Legislature Regular session ends
June 5 - 19, 2025 | Proofing + alterations + approval of 2025 campaign materials — by SWFs and LCMs | SWF, LCM
2025-06-13 | SPC MEETING (optional): Campaign planning and miscellaneous topics as needed | SPC
2025-06-19 | Emancipation Day (Skeleton crew required at state offices)
June 23 - 25, 2025 | Review + approval of finalized 2025 campaign materials — by SCM | SCM
2025-06-26 | "Send to Print" deadline for centralized printed materials | SCM
2025-06-30 | Second distribution of 2025 SECC funds to be finalized | LCM
During July | SCM-provides an online giving software training for all Local Campaign Managers | SCM, LCM
2025-07-04 | Independence Day
2025-07-11 | SPC MEETING (optional): Campaign planning and miscellaneous topics as needed | SPC
2025-07-03 | All centralized ordering printed campaign materials sent to printers | SCM
During August | A statewide online giving software training led by Statewide Campaign Manager will be held and open to statewide campaign coordinators and local campaign coordinators from all regions | SCM
First week of August | Campaign materials delivered to Local Campaign Managers (centralized ordering) | SPC
August 1 - 29, 2025 | Employee campaign coordinator trainings in all local regions | LCM
2025-08-08 | SPC MEETING & PLANNING RETREAT: Campaign planning and miscellaneous topics | SPC
2025-08-27 | LBJ Day (Skeleton crew required at state offices)
September 1 - October 31, 2025 | Annual State Employee Charitable Campaign (statutorily authorized time to ask state or higher education employees for a charitable payroll deduction) | ALL
2025-09-01 | Labor Day (Offices closed)
2025-09-22 | Rosh Hashanah (Optional state holiday)
2025-09-26 | SPC MEETING: Campaign items and miscellaneous topics as needed | SPC
2025-09-30 | Third distribution of 2025 SECC funds to be finalized | LCM
2025-10-02 | Yom Kippur (Optional state holiday)
2025-10-27 | Final campaign result/report template due to LCMs | SCM
2025-11-06 | Deadline for all online agencies to turn in all paper payroll deduction forms to their Local Campaign Manager for data entry into online software | LCM
2025-11-07 | Deadline for all non-online agencies to turn in all paper payroll deduction forms to their respective payroll offices for data entry | LCM
2025-11-07 | SPC MEETING: Approval of charity, SCM, and LCM applications for the next campaign year | SPC
2025-11-11 | Veterans Day (State offices closed)
2025-11-13 | Deadline for Local Campaign Managers to enter all paper payroll pledges (only for all online agencies) | LCM
2025-11-14 | Final payroll report due from State Campaign Manager to CPA for all online state agencies on the CAPPS system. | SCM
2025-11-27 | Thanksgiving Day (State offices closed)
2025-11-28 | Day After Thanksgiving (State offices closed)
December 1, 2025 - January 23, 2026 | Prepare final campaign results reporting for SCM | LCM
2025-12-05 | Application announcement is posted by current LCMs for charities interested in serving as a 2026 Local Campaign Manager | LCM
2025-12-24 | Christmas Eve Day
2025-12-25 | Christmas Day (State offices closed)
2025-12-26 | Christmas holiday (State offices closed)
2025-12-30 | Final distribution of 2024 SECC funds | LCM
2026
2026-01-01 | New Year's Day (State offices closed)
2026-01-05 | Request is posted for applications from charities interested in participating in the SECC as statewide federations or members. Note: 2026 is the first of two years in which applicable federation and federation member charities may submit a re-certified application. | SCM
2026-01-19 | Martin Luther King, Jr. Day (State offices closed)
2026-01-12 | SAC MEETING: Review proposed 2026 SCM campaign plan, timeline, and budget | SAC
2025-01-23 | Deadline for Local Campaign Managers to submit final 2025 campaign results report to State Campaign Manager | LCM
2026-02-13 | SPC MEETING: Review SAC recommendation of SCM campaign plan, timeline, budget, and determine SCM, 2025 results, Sunset and Legislative planning, Local Campaign Manager applications & budgets, Local Employee Committee members, local region names & boundaries, charity application review training | SPC
* State Policy Committee and State Advisory Committee meeting dates and agenda subject to change
ECC | Employee Campaign Coordinator
LCM | Local Campaign Manager
LEC | Local Employee Committee
LOCAL CHARITIES | Local Charity Federations and Unaffiliated Charities
SAC | State Advisory Committee
SCM | State Campaign Manager
SPC | State Policy Committee
STATEWIDE CHARITIES | Statewide Charity Federation
Note on A16: gbennett: By law, the state campaign manager shall ensure that the state policy committee, the state advisory committee, and the comptroller receive the statewide campaign report not later than February 5th of the calendar year following the calendar year in which the campaign covered by the report ended. If February 5th is not a workday, then the first workday after February 5th is the deadline.